CREATING A PUBLIC UTILITY PARC IN THE “ION CREANGA” NEIGHBORHOOD

PROJECT FINANCED THOUGH THE 2007 – 2013 ROP

PRIORITY AXIS 1 – SUPPORTING THE SUSTAINABLE DEVELOPMENT OF CITIES – URBAN GROWTH POLES, KEY AREA OF INTERVENTION 1.1 – INTEGRATED PLANS OF URBAN DEVELOPMENT, SUB-AREA – URBAN CENTERS

DISTRCT 2 OF THE MUNICIPALITY OF BUCHAREST

December 7th, 2011

Pagina 2

District 2 of the Municipality of Bucharest signed on June 2nd, 2011 the financing agreement no. 1692 with the Ministry of Regional Development and Tourism

The total value is of 9,705,063.16 Lei out of which:

The contribution of the European Union: 6,073,383.89 Lei

The contribution of the Romanian Government: 1,258,517.01 Lei

The contribution of the Beneficiary: 2,373,162.26 Lei

Project implementation duration: 12 months

Pagina 3

Creanga neighborhood

Surface – 1.96 ha

Muntii Buzaului street

Juverdeanu street

LOCATION OF PROJECT IMPLEMENTATION

Pagina 4

The general objective of the project:

Increasing the quality of life and the degree of social cohesion by improving the urban infrastructure in District 2 of the Municipality of Bucharest – the “Ion Creanga” neighborhood

Specific objective:

Improving the level of environmental protection

Pagina 5

At the date of signing the financing agreement the surface allocated to the park of 1.96 ha was abandoned and transformed into a location for unauthorized waste disposal by the population.

Pagina 7

The lack of recreational areas, the uncontrolled waste disposal which could lead to endangering the health of the population through environmental pollution (air, soil, underground water) and the lack of safety while passing through the area, led to taking the decision of developing a park, decision which is now in the stage of being materialized.

Pagina 7

Project potential beneficiaries:

The target group is the neighborhood population of approximately 25,000 inhabitants, all age groups included. At present the green surface corresponding to an inhabitant is of 20 m2, which falls under the European norms (in accordance with the Law no. 24 / January 2007 and GEO no. 114 / October 17th, 2007).

Pagina 8

Main works to be executed (1):

- Rehabilitating the existing vegetation and planting dendrological material having a surface of 16,500 m2,

- Alleys of stabilized sand having a surface of 1,100 m2,

- Landscape with a visual impact;

- Setting up a solar powered lighting installation with a length of 2 km;

- Setting up an automated irrigation network which will allow the irrigation of 16,000 m2;

- Setting up 2 playgrounds with a surface of 1045 m2 equipped with swing for children, labyrinth, playhouses etc.;

Pagina 9

Main works to be executed (2):

- Setting up a recreational area

- Setting up  bicycle lanes

- Fencing with filling material WPC = 772 ml and installing 8 access gates.

- Installing drinking water fountains = 8 pieces

- Installing bathrooms = 8 pieces

- Installing 4 electronic information desks and 4 billboards and a video surveillance system with 8 video cameras

- Equipping with qualitative park furniture, 50 benches,

- Equipping the park with 30 selective waste collection bins

Pagina 10

The works started on July 15th, 2011, when the location was handed over and the order for starting the works was issued to company that won the tender.

The works are being carried out in accordance with the execution graph, having the possibility of finalizing them earlier than expected.

Contracted period of performance: 8 months since issuing the order for starting the works, namely march 2012

Pagina 11

After having signed the financing agreement, District 2 of the Municipality of Bucharest, in its capacity as Beneficiary, started all the public procurement procedures and signed all the contracts with the economic operators for:

- Advisory services for the implantation of the project;

- Works execution

- Purchase of equipment;

- Site coordination;

- Information and advertising services;

- Services for auditing expenses

Pagina 12

Up to the present moment the following works have been executed:

- Land planning;

- Environmental facilities consisting in cleaning the site, trimming the existing vegetation, cleaning and eliminating the degraded vegetation;

- The infrastructure works have been accomplished in a ratio of 80% consisting of water supply networks, public lighting network, video surveillance network;

- Bicycle lanes, skate park platform, and multi sports courts were set up (692 m2)

Pagina 13

The project shall provide a higher quality of public areas, improved environmental indicators, so that the green area shall function as a leisure and relaxation nucleus for the citizens of the “Creanga” neighborhood.

Pagina 14

REGIO PROJECTS BEING IMPLEMENTED

Priority Axis 1 – Supporting the sustainable development of cities – urban growth poles

Key area of intervention 1.1 – Integrated plans of urban development; Sub-area: Urban centers

- Integrated plan for the urban development of the Baicului area

- Modernizing the streets in the Baicului area (24 streets)

- Structural design and landscaping in

- Video surveillance system and information management in order to increase the safety and prevent crime in the Baicului area

Pagina 15

REGIO PROJECTS BEING IMPLEMENTED

Priority Axis 1 – Supporting the sustainable development of cities – urban growth poles

Key area of intervention 1.1 – Integrated plans of urban development; Sub-area: Urban centers

- Integrated plan for the urban development of the Creanga area

- Creating a public utility park in the “Ion Creanga” neighborhood

- Video surveillance system and information management in order to increase the safety and prevent crime in the “Creanga” area

Pagina 16

REGIO PROJECTS BEING IMPLEMENTED

Priority Axis 3 – Improving the social infrastructure

Key area of intervention 3.4 Rehabilitating / modernizing / developing and equipping the pre-university and university infrastructure for the continuous vocational training

- Rehabilitating, modernizing and equipping the pre-university educational infrastructure of the “Iulia Hasdeu” National College

- Rehabilitating, modernizing and equipping the pre-university educational infrastructure of the “C.A. Rosetti” high school

Pagina 17

CITY HALL OF DISTRICT 2

11-13 Chiristigiilor Street

Phone no.: 021.209.60.00

Fax no.: 021.209.62.82